Event Risk Management Plan

| Risk Assessment ~ All columns MUST be completed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| - Hazard / Source* List individual tasks or activities | - Risks * Identify the potential risks associated with each task / activity. | - Risk Rating* Before Controls - Low - Medium - High - Extreme | - Risk Controls * Controls to address identified risks | - Risk Rating * After Controls - Low - Medium - High - Extreme | - Responsibility * Name of person responsible for implementing risk controls |
| Food | Food poisoning | Medium | - Ensure SEL staff have appropriate food licenses. - SEL has adequate refrigeration / cooling for their requirements. - Adequate hand washing facilities are available for staff. | Low | Stadium |
| Court Surface | Floors slippery due to liquid spill, food spill or sweat | Medium | - No food/drink allowed in halls except water. - Ensure towels are at each scorebench - Signage around venue to ensure all spills are wiped up | Medium | Stadium |
| Venue Set up | Injury due to close set up of courts | Medium | - Apply the Field of Play Layout parameters (Appendix A) - Nets lowered between courts where possible. - Signage alerting spectators to be aware of volleyballs leaving the field of play | Low | Stadium, Tournament Director |
| Game play | Injury during gameplay | Low | - Ensure hazards identified above a mitigated. - Insurance - Venue Set Up - Rules of play | Low | Tournament Director |
| Lost property | Items being stolen or lost, especially Volleyballs | High | - Branding each Volleyball with VVI - Complete a ball count at the start and end of each day. - Ensure match ball comes back to hall supervisor desk with scoresheet so that the next referee or duty team can collect - Tournament Director to be notified if a ball has been lost - Lost items to be taken to Tournament Office (Rangers Room) | High | Tournament Director, VV Staff |
| Financial | Event runs overbudget, profits are less, or event runs into the red | Medium | - Adjust Budget of another competition/event to allow for everything to breakeven | Low | Tournament Director, Operations Manager |
| Staffing | Staff turn up late or do not arrive at all | Low | - Staff in attendance take on extra tasks where possible - Staffing plan caters for risk and tasks are resassigned | Low | Tournament Director |
| Bins | Overflowing bins | Medium | - Schedule cleaners throughout the day of the event to ensure venue cleanliness | Low | Stadium |
| Game Management | Duty Teams skip completing their duty either without knowledge of duty or on purpose | Medium | - Position a staff member at the exit halfway through the last pool games to sign teams out | Low | Tournament Director, VV Staff |
| Game Management | Teams do not show up for scheduled game or are late | Medium | - Communication of fixtures to team managers - Fixtures printed and available throughout the venue - Follow in accordance with tournament regulations and the game is a forfeit - Use of Exposure for fixtures | Low | Tournament Director, VV Staff |
| Safety | Athletes climbing up on the shed roof to retrieve ball that gets stuck | High | - Place signs on the sheds with details of how to retrieve ball | Medium | Stadium, VV staff, Teachers, Spectators |

Appendix A – Field of Play

Public Liability Insurance

Have you provided evidence of appropriate Public Liability Insurance for your event? *		  Own Policy   	☐ Cover under Council’s Policy

Have Public Liability Insurance Certificates of Currency been provided from all external parties? *	  Yes   		☐ No

Declaration

| I verify that I have, to the best of my knowledge endeavored to anticipate all possible risks relevant to the above event and will ensure all controls listed above are implemented. |  |  |  |
| --- | --- | --- | --- |
| Event Organiser: | Matthew Maiolo | Organisation: | Volleyball Victoria Inc |
| Signature: | M Maiolo | Date: | 19/02/2026 |